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	Milestones
	Date

	Mobilization & Laydown Yard Establishment (as load restrictions allow)
	01-May-2019

	Testing and Commissioning Plan Due
	01-Aug-2019

	Commence Delivery of WTGs
	Per Ex C(iii)

	Scheduled Final Completion Date
	29-Nov-2019

	Preliminary Public Road Completion
	15-Jul-2019

	Final Public Road Completion
	14-Nov-2019

	Preliminary Access Road Completion
	

	1st Circuit
	15-Jun-2019

	2nd Circuit
	01-Jul-2019

	3rd Circuit
	20-Jul-2019

	4th Circuit
	06-Aug-2019

	Final Access Road Completion
	

	1st Circuit
	26-Sep-2019

	2nd Circuit
	11-Oct-2019
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	3rd Circuit
	25-Oct-2019

	4th Circuit
	15-Nov-2019

	Main Step-Up Transformer Placed
	15-Aug-2019

	Control Building Pad Placed
	01-Aug-2019



2 GUARANTEED MILESTONES

	Guaranteed Dates
	Date

	Clearing Completion (tree removal for environmental purposes by other Contractor)
	29-Nov-2018

	Clearing Completion (other tree removal required to construct project, may be performed by other Contractor)
	1-Jun-2019

	Clearing of area surrounding t-line tap (To facility Hydro One work, may be performed by other Contractor)
	09-May-2019

	Completion of 230 kV substation entrance structure (To facility Hydro One work, may be performed by other Contractor)
	09-May-2019

	Complete construction of a 6m wide access road to the location of Hydro One’s mid-span (To facility Hydro One work, may be performed by other Contractor)
	09-May-2019

	Turbine Foundation and Crane Pad Completion
	

	1st Circuit[1]
	15-Jul-2019

	2nd Circuit[1]
	01-Aug-2019

	3rd Circuit[1]
	20-Aug-2019

	4th Circuit[1]
	06-Sep-2019

	Collection Circuit Completion
	

	1st Circuit
	01-Aug-2019

	2nd Circuit
	22-Aug-2019

	3rd Circuit
	12-Sep-2019

	4th Circuit
	03-Oct-2019

	Mechanical Completion
	

	1st Circuit[1]
	11-Sep-2019

	2nd Circuit[1]
	27-Sep-2019

	3rd Circuit[1]
	15-Oct-2019

	4th Circuit[1]
	31-Oct-2019





	Meteorological Tower Construction Completion (2X)
	01-Aug-/2019

	Substation Completion
	15-Oct-2019

	Project High Voltage Completion
	31-Oct-2019

	O&M Building Completion
	15-Oct-2019

	Substantial Completion
	12-Nov-2019



[1] List out individual turbine on each particular circuit in the milestone schedule which allows us to receive certificates and assures no change to the language in the agreement.
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